## Slide 1
Workshop
Task Management Process
AI-powered planning and execution with SCUD
From PRD to parallel execution

## Slide 3
Installation
Option 1: NPM / PNPM
pnpm add -g scud-task
# or: npm install -g scud-task
Option 2: Cargo
cargo install scud-cli
Initialize
cd your-project && scud init
Prerequisites
Node.js 18+ (npm) or Rust (cargo)
AI API key (xAI, Anthropic, OpenAI)
What you get
+
Fast Rust CLI binary
+
.scud/ directory for task storage
+
SCG format (compact text)
+
Claude Code slash commands

## Slide 4
INSPIRATION
Claude Task Master
AI-powered task management for complex development projects
github.com/eyaltoledano/claude-task-master
PRD Parsing
Parse requirements docs into structured tasks with AI
Multi-Model
Supports Claude, GPT, Gemini, xAI, OpenRouter
MCP Server
Integrates with Cursor, VS Code, Windsurf
Research Mode
Web research with project context
Task Master Workflow
1
Write PRD
2
Initialize
3
Generate Tasks
4
Ask "Next?"
5
Implement
6
Update Status

## Slide 5
SCUD: What's Different?
Task Master
JavaScript
Storage Format
JSON files
Dependency Model
Simple blockers
Parallel Planning
Manual
Runtime
Node.js
SCUD
Rust
Storage Format
SCG (compact text)
Dependency Model
Full DAG with edges
Parallel Planning
Automatic waves
Runtime
Native binary
SCUD Advantages
Fast native CLI
Explicit dependency graph
Wave-based parallelism
Agent orchestration

## Slide 6
SCG: SCUD Graph Format
INSPIRED BY JAMS
Token-efficient, human-readable task storage
nikolai.fyi/jams — Nikolai Mushegian (DeFi pioneer)
# SCUD Graph v1
# Phase: auth
@nodes
auth:1 | Design auth | D | 5 | H
auth:2 | JWT tokens | P | 3 | M
auth:3 | Rate limits | P | 3 | L
@edges
auth:2 -> auth:1
auth:3 -> auth:2
@details
auth:1 | description |
Design REST endpoints...
JAMS Philosophy
"Actually Minimalist JSON Alternative" — Most alternatives have longer specs than JSON itself. JAMS builds on JSON's foundation, reducing quote noise while keeping parsing simple.
SCG Design Goals
Graph-native structure with explicit @nodes and @edges. Single-char status codes (P/I/D/B). Pipe-delimited rows. Git-friendly diffs.
Benefits
Compact text format. Human-editable. Git-friendly diffs. Reduced context for LLMs.

## Slide 7
Agent Skills & Commands
Teaching AI agents how to use the SCUD CLI effectively
SKILL FILES
SKILL.md
Entry point - when to use SCUD, essential commands, workflow overview
task-commands.md
Full CLI reference - tags, viewing, status updates, AI commands
graph-concepts.md
DAG structure, SCG format, waves algorithm, complexity scoring
Location:.claude/skills/scud-tasks/
SLASH COMMANDS
/scud:list
/scud:show
/scud:status
/scud:next
/scud:waves
/scud:stats
Why Skills Matter
+
Agents understand task structure without prompting
+
Consistent command usage across sessions
+
Proper status updates after completing work
+
Awareness of dependencies and waves
Location:.claude/commands/scud/

## Slide 8
STEP 1
scud init
Initialize SCUD in your project directory
$ scud init
Created .scud/
Created .scud/tasks/tasks.scg
Created .scud/config.toml
SCUD initialized successfully!
Creates .scud/ directory for task storage
Configures AI provider (xAI, Anthropic, OpenAI)
Ready to parse your first PRD

## Slide 9
STEP 2
scud parse
Convert PRD to structured tasks
$ scud parse feature.md --tag auth
AI-Powered - Extracts tasks from natural language
Dependencies - Auto-detects task relationships
Complexity - Fibonacci estimates (1,2,3,5,8...)
OUTPUT: .scud/tasks/tasks.scg
@nodes
auth:1 | Design auth | P | 5 | H
auth:2 | JWT tokens | P | 3 | H
auth:3 | OAuth flow | P | 5 | M
auth:4 | Rate limit | P | 3 | M
@edges
auth:2 -> auth:1
auth:3 -> auth:1
auth:4 -> auth:2

## Slide 10
STEP 3
scud expand
Break complex tasks into actionable subtasks
$ scud expand
PROCESSES IN PARALLEL
auth:1
Design auth (13pts) -> 3 subtasks
auth:4
OAuth flow (13pts) -> 4 subtasks
api:2
API routes (21pts) -> 5 subtasks
->
Result
12 new subtasks
All complex tasks broken down

## Slide 11
STEP 4
scud waves
Plan parallel execution based on dependencies
$ scud waves --tag auth
WAVE 1
auth:1.1 Define schema
auth:1.2 Plan tokens
RUN IN PARALLEL
WAVE 2
auth:1.3 API design
auth:2 JWT tokens
RUN IN PARALLEL
WAVE 3
auth:3 OAuth flow
auth:4 Rate limit
RUN IN PARALLEL
6
Total Tasks
3
Waves
2x
Speedup

## Slide 12
STEP 4: VALIDATE
Smart Review with Opus
Use a stronger model to validate expanded tasks against the PRD
OPUS 4.5
> /cl:create_plan_nt
@.scud/tasks/tasks.scg
@.scud/docs/prd/h-init.md
# Prompt:
Create an implementation plan based
on the tasks in PRD. Make sure tasks
and dependencies make sense. We want
to run in parallel as much as we can.
Usescud waves to see the plan.
SCG
Task Graph
PRD
Requirements
WAV
Parallel Plan
Why Review with a Smarter Model?
SCUD uses fast models for parsing. A stronger model (Opus/GPT-5) catches gaps, validates dependencies, and refines the plan before execution.
Review Checklist
+
All PRD requirements have tasks
+
Dependencies are correctly ordered
+
Parallel waves are well-structured
+
No missing edge cases or tests
+
Complexity estimates are realistic

## Slide 13
Complete Workflow
1
Init
scud init
->
2
Parse
scud parse
->
3
Expand
scud expand
->
4
Waves
scud waves
->
5
Execute
scud next
Task Execution
scud next
Find next ready task
scud set-status <id> in-progress
Mark task as started
scud set-status <id> done
Complete the task
Visibility
scud list
List all tasks
scud stats
Show progress stats
scud view
Open web dashboard

## Slide 14
OPEN QUESTION
Is any of this even necessary?
As models improve, hyper-granular task breakdown may add more rigidity than value. Finding the sweet spot between thorough planning and over-constraining remains an open challenge.
Thorough Planning
Over-Constrained
?
sweet spot shifts as models evolve